## 🗺 Roadmap
🐾 BarkBowl — Product Roadmap
Last updated: June 2026 ¦ Status: Active Development
Phase / Feature | Category | Status | Priority | Effort (wks) | Owner | Depends On | Notes
✅ Phase 0 — MVP (Shipped)
Database & Infrastructure Setup | Platform | ✅ Done | — | — |  | — | schema.sql, seed.sql, RLS, mock mode
User Authentication | Auth | ✅ Done | — | —
Dog Profile Setup | Onboarding | ✅ Done | — | —
Pet Type Onboarding | Onboarding | ✅ Done | — | —
Ready-Made Meals | Meals | ✅ Done | — | —
Build Your Own Bowl | Meals | ✅ Done | — | —
Cart & Checkout | Commerce | ✅ Done | — | —
Subscription Options | Commerce | ✅ Done | — | —
Order History & Tracking | Orders | ✅ Done | — | —
React Web App | Platform | ✅ Done | — | —
Expo Mobile App (iOS/Android) | Platform | ✅ Done | — | —
🔧 Phase 1 — Commerce (Q3 2026)
Stripe Payment Integration | Commerce | 🔜 Up Next | High | 2
Post-Delivery Reviews | Engagement | 🔜 Up Next | High | 2
Push Notifications | Engagement | 📋 Planned | High | 4
Real-Time Delivery Tracking | Orders | 📋 Planned | Medium | 4
Promo Codes & Discounts | Commerce | 📋 Planned | Medium | 4
🤖 Phase 2 — Personalization (Q4 2026)
AI Meal Recommendations | Meals | 📋 Planned | High | 4
Loyalty Points System | Engagement | 📋 Planned | High | 4
Referral Program | Growth | 📋 Planned | High | 4
Multi-Dog Household Support | Profile | 📋 Planned | Medium | 4
In-App Feeding Reminders | Engagement | 📋 Planned | Medium | 4
Smart Reorder Prediction | Commerce | 📋 Planned | Medium | 4
🏥 Phase 3 — Health & Scale (Q1 2027)
Admin Dashboard | Platform | 📋 Planned | High | 4
Vet/Nutritionist Consultation | Health | 📋 Planned | High | 4
Weight & Health Tracking | Health | 📋 Planned | Medium | 4
Birthday & Seasonal Meals | Meals | 📋 Planned | Low | 4
Pet Health Records Integration | Health | 📋 Planned | Low | 4
🐱 Phase 4 — Cat Meals Launch (Q2 2027)
Cat Meal Menu | Meals | 📋 Planned | High | 4
Cat Profile & Onboarding | Onboarding | 📋 Planned | High | 4
Cat Nutrition Engine | Meals | 📋 Planned | High | 4
Cat Subscription Plans | Commerce | 📋 Planned | Medium | 4
Local Pet Store Partnerships | Growth | 📋 Planned | Low | 4

## 📋 Feature Details
🐾 BarkBowl — Feature Details & Task Breakdown
Feature | Phase | Priority | Category | Frontend Tasks | Backend Tasks | DB Changes | Dependencies | Effort (wks) | Success Metric
Stripe Payment Integration | Phase 1 | High | Commerce | Payment form UI, card input, success/fail screens | Stripe webhook handler, payment intent API, order confirmation | orders: add payment_intent_id, payment_status columns | Cart & Checkout (done) | 3 | 95%+ payment success rate, <3s checkout flow
Post-Delivery Reviews | Phase 1 | High | Engagement | Star rating modal after delivery, review history screen | Reviews CRUD API, rating aggregation | New: reviews table (order_id, rating, comment, dog_reaction) | Order delivery status | 2 | >40% review completion rate within 48hrs of delivery
Push Notifications | Phase 1 | High | Engagement | Permission prompt, notification preferences screen | Expo push token storage, notification trigger service | users: add push_token, notification_prefs columns | Order tracking statuses | 2 | >60% opt-in rate, delivery notification open rate >50%
Real-Time Delivery Tracking | Phase 1 | Medium | Orders | Live map view, animated status timeline | Supabase Realtime subscription, driver location API | orders: add driver_lat, driver_lng, eta columns | Push Notifications | 3 | Customer support tickets re: delivery reduced by 30%
Promo Codes & Discounts | Phase 1 | Medium | Commerce | Promo code input at checkout, discount display in cart | Promo code validation API, usage tracking | New: promo_codes table (code, discount_pct, max_uses, expires_at) | Stripe Payment Integration | 2 | Promo redemption rate >15% of eligible orders
AI Meal Recommendations | Phase 2 | High | Meals | "Recommended for Bella" cards on home, explanation chips | ML recommendation engine (dog profile + order history), scoring API | New: recommendations table, meal_scores view | Dog Profile, Order History, 50+ orders of data | 5 | Recommended meals add-to-cart rate >25% vs 10% baseline
Loyalty Points System | Phase 2 | High | Engagement | Points balance widget, rewards catalog, redeem flow | Points ledger API, reward redemption, expiry jobs | New: loyalty_points table, rewards table, redemptions table | Stripe Payment Integration | 4 | Monthly active subscribers +20%, churn rate -15%
Referral Program | Phase 2 | High | Growth | Referral share screen, unique link generator, reward tracker | Referral tracking API, reward credit on first order | New: referrals table (referrer_id, referee_id, status, credited_at) | Stripe Payment Integration, Loyalty Points | 3 | 10% of new signups via referral within 3 months of launch
Multi-Dog Household Support | Phase 2 | Medium | Profile | Dog switcher in nav, per-dog cart, profile management improvements | Update all order APIs to support multiple dog selections | No schema change — dogs table already supports multiple rows per user | Dog Profile (done) | 2 | Avg dogs per account >1.3 among active subscribers
In-App Feeding Reminders | Phase 2 | Medium | Engagement | Reminder setup screen, time picker, snooze options | Scheduled push notification service, reminder CRUD | New: feeding_reminders table (dog_id, time, frequency, enabled) | Push Notifications | 2 | >35% of users set at least one feeding reminder
Smart Reorder Prediction | Phase 2 | Medium | Commerce | "Running low?" banner on home, one-tap reorder | Consumption prediction model based on portion + dog weight | No schema change — uses existing orders + dog weight | AI Meal Recommendations, 3+ orders per user | 3 | Reorder prompt CTR >30%, subscription conversion +10%
Admin Dashboard | Phase 3 | High | Platform | Web-only admin app: orders table, menu editor, user management | Admin auth (role-based), analytics endpoints, menu CRUD | New: admin_roles table; meals table gains admin edit fields | All Phase 1 features | 6 | Menu update time <5 min, order issue resolution <2hrs
Vet/Nutritionist Consultation | Phase 3 | High | Health | Book consultation flow, chat interface, prescription meal plans | Booking API, calendar integration, vet profile management | New: vets table, consultations table, prescription_plans table | Dog Profile, AI Meal Recommendations | 6 | BarkBowl Plus subscription revenue >15% of total MRR
Weight & Health Tracking | Phase 3 | Medium | Health | Weight log screen, progress chart, goal setting | Weight history API, trend analysis, meal adjustment suggestions | New: weight_logs table (dog_id, weight_lbs, logged_at, notes) | Dog Profile (done) | 3 | >25% of active dog profiles have at least 4 weight entries
Birthday & Seasonal Meals | Phase 3 | Low | Meals | Birthday banner on dog's birthday, seasonal menu section | Date-based meal surfacing logic, seasonal tagging | meals: add seasonal_tag, available_from, available_until columns | Ready-Made Meals (done) | 2 | Seasonal meal sell-through rate >70% of stock
Cat Meal Menu | Phase 4 | High | Meals | Cat meals section, cat-specific filters, feline nutrition labels | Cat meal CRUD, cat nutrition validation rules | meals: add pet_type column; New: cat_ingredients table | Cat Profile & Onboarding | 4 | Cat waitlist conversion rate >50% on launch
Cat Profile & Onboarding | Phase 4 | High | Onboarding | Cat profile form (name, breed, age, indoor/outdoor), cat onboarding flow | Cat profile API (extends dogs table with pet_type='cat') | dogs: pet_type column already planned; add indoor_outdoor field | Pet Type Onboarding (done) | 2 | Cat profile completion rate >80%
Cat Nutrition Engine | Phase 4 | High | Meals | Taurine badge, cat-specific nutrition score, vet-approved labels | Cat nutrition validation (taurine, arachidonic acid rules), scoring API | New: cat_nutrition_rules table | Cat Meal Menu, Vet/Nutritionist Consultation | 5 | 0 nutrition-related customer complaints post-launch

## ⚡ Sprint Tracker
🐾 BarkBowl — Sprint Tracker
Task | Feature | Type | Assignee | Sprint | Status | Est. Days | Notes
Design payment form UI | Stripe Integration | Frontend |  | Sprint 1 | To Do | 2
Implement Stripe Elements | Stripe Integration | Frontend |  | Sprint 1 | To Do | 3 | Use @stripe/stripe-react-native
Build payment intent backend | Stripe Integration | Backend |  | Sprint 1 | To Do | 2
Add Stripe webhook handler | Stripe Integration | Backend |  | Sprint 1 | To Do | 2 | Handle payment_succeeded, failed
DB migration: payment columns | Stripe Integration | Database |  | Sprint 1 | To Do | 1
End-to-end checkout test | Stripe Integration | QA |  | Sprint 1 | To Do | 1
Post-delivery review modal | Reviews | Frontend |  | Sprint 2 | To Do | 2 | Trigger 2hrs after delivered status
Star rating + dog reaction UI | Reviews | Frontend |  | Sprint 2 | To Do | 1
Reviews API (CRUD) | Reviews | Backend |  | Sprint 2 | To Do | 2
DB: reviews table migration | Reviews | Database |  | Sprint 2 | To Do | 1
Push permission prompt | Push Notifications | Frontend |  | Sprint 2 | To Do | 1
Notification preferences screen | Push Notifications | Frontend |  | Sprint 2 | To Do | 1
Expo push token backend storage | Push Notifications | Backend |  | Sprint 2 | To Do | 1
Order status notification triggers | Push Notifications | Backend |  | Sprint 2 | To Do | 2
Dog profile feature engineering | AI Recommendations | Backend |  | Sprint 4 | To Do | 3 | Breed, age, weight, allergies vectors
Order history embedding model | AI Recommendations | Backend |  | Sprint 4 | To Do | 4
Recommendation scoring API | AI Recommendations | Backend |  | Sprint 4 | To Do | 3
"For Bella" UI cards on home | AI Recommendations | Frontend |  | Sprint 5 | To Do | 2
Points balance widget | Loyalty Points | Frontend |  | Sprint 5 | To Do | 1
Rewards catalog screen | Loyalty Points | Frontend |  | Sprint 5 | To Do | 2
Points ledger backend | Loyalty Points | Backend |  | Sprint 5 | To Do | 3 | Earn on order, burn on reward
DB: loyalty tables | Loyalty Points | Database |  | Sprint 5 | To Do | 1
Admin auth & role system | Admin Dashboard | Backend |  | Sprint 7 | To Do | 3
Orders management table | Admin Dashboard | Frontend |  | Sprint 7 | To Do | 3 | Web only
Menu editor (meals + ingredients) | Admin Dashboard | Frontend |  | Sprint 8 | To Do | 4
Analytics overview page | Admin Dashboard | Frontend |  | Sprint 8 | To Do | 3

## 📊 KPIs & Metrics
🐾 BarkBowl — KPIs & Success Metrics
Metric | Category | Target | Current | Phase | Notes
Monthly Active Users (MAU) | Growth | 5,000 by Q4 2026 | — | Phase 1
Subscriber Conversion Rate | Commerce | >30% of orders | — | Phase 1 | One-time → subscription
Monthly Recurring Revenue (MRR) | Commerce | $50K by Q4 2026 | — | Phase 1
Average Order Value (AOV) | Commerce | >$35 | — | Phase 0
Churn Rate (monthly) | Retention | <8% | — | Phase 1 | Subscription cancellations
Payment Success Rate | Commerce | >95% | — | Phase 1 | Stripe integration target
Review Completion Rate | Engagement | >40% within 48hrs | — | Phase 1 | Post-delivery prompt
Push Notification Opt-in | Engagement | >60% | — | Phase 1
AI Rec Click-Through Rate | Meals | >25% | — | Phase 2 | vs 10% baseline for non-personalized
Loyalty Points Redemption | Engagement | >20% of earners | — | Phase 2 | Monthly
Referral Program Conversion | Growth | >10% of signups | — | Phase 2 | Within 3 months of launch
Avg Dogs Per Account | Profile | >1.3 | — | Phase 2 | Multi-dog household indicator
BarkBowl Plus Attach Rate | Commerce | >15% of MAU | — | Phase 3 | Vet consultation subscription
Cat Waitlist Conversion | Growth | >50% | — | Phase 4 | Waitlist → paying customers
NPS Score | Retention | >60 | — | Ongoing | Target promoter-heavy
Delivery Issue Rate | Operations | <2% | — | Ongoing | Late, wrong, or damaged orders