## Roadmap
🐾 PawBowl — Project Roadmap
Phase | Feature | Priority | Status | Sprint | Owner | Notes
Phase 0 Database & Infra | Database Schema v2 (Supabase/PostgreSQL) | Critical | Done | S0 | Backend | pet_types, pets, ingredients, meals, meal_ingredients, custom_recipes, orders, pet_allergies, pet_health_goals, ingredient_rules, nutrition_rules, RLS policies
Phase 0 Database & Infra | Seed Data (meals, ingredients, rules) | Critical | Done | S0 | Backend | 7 pre-made meals with real macro data, 20+ ingredients, ingredient safety rules
Phase 0 Database & Infra | Supabase Auth Setup | Critical | In Progress | S0 | Backend | Email/password auth, handle_new_user trigger, profiles table auto-create
Phase 1 MVP Core | Sign In / Sign Up Screens | Critical | Done | S1 | Mobile | Email/password, toggle log-in vs create account, redirect to onboarding if new user
Phase 1 MVP Core | Onboarding Flow (Pet Type → Pet Setup) | Critical | Done | S1 | Mobile | Pet type picker → dog setup (name, breed, age, weight, activity) → cat waitlist
Phase 1 MVP Core | Browse Pre-Made Meals | Critical | Done | S1 | Mobile | List with filter by life stage, badge, calories; emoji art; horizontal scroll
Phase 1 MVP Core | Build-a-Bowl Wizard | Critical | Done | S1 | Mobile | 4-step wizard: protein → base → vegetables → boosters; live calorie counter
Phase 1 MVP Core | Cart & Checkout | Critical | Done | S1 | Mobile | Cart context, quantity adjust, order total, checkout form, mock order submit
Phase 1 MVP Core | Order History | High | Done | S1 | Mobile | List past orders, status indicator, reorder shortcut
Phase 1 MVP Core | Pet Profile (CRUD) | High | Done | S1 | Mobile | Add/edit/delete pets; name, breed, birth date, weight, sex, activity level, BCS
Phase 2 Personalization | Pet Allergies & Health Goals | High | Planned | S2 | Mobile/BE | Normalized pet_allergies + pet_health_goals tables; UI to set per pet
Phase 2 Personalization | Meal Recommendations Engine | High | Planned | S2 | Backend | Filter meals by pet allergies, health goals, life stage, activity level
Phase 2 Personalization | Nutrition Dashboard | Medium | Planned | S2 | Mobile | recipe_nutrition view; protein/fat/fiber/calorie rings; AAFCO targets
Phase 2 Personalization | Ingredient Safety Warnings | High | Planned | S2 | Mobile/BE | ingredient_rules enforcement in bowl builder; warn on spinach over-dose etc.
Phase 3 Subscriptions | Subscription / Auto-Reorder | High | Planned | S3 | Full Stack | Frequency selector, next-delivery date, pause/cancel, billing via Stripe
Phase 3 Subscriptions | Delivery Tracking | Medium | Planned | S3 | Full Stack | Status timeline, estimated delivery, push notifications
Phase 4 Social & Loyalty | Reviews & Ratings | Medium | Planned | S4 | Full Stack | Per-meal star rating + comment; average displayed on meal card
Phase 4 Social & Loyalty | Loyalty Points & Referrals | Low | Planned | S4 | Full Stack | Earn points per order; referral code; redeem for discounts
Phase 5 Cat Support | Cat Meals & Ingredients | Medium | Planned | S5 | Full Stack | ingredient_pet_types unlocks cat-safe subset; separate meal catalogue

## Feature Details
🐾 PawBowl — Feature Details
Feature | User Story | Tasks | Acceptance Criteria | Dependencies | Effort (pts) | Metrics
Database Schema v2 | As a dev, I need a normalized schema that supports multiple pet types, allergy tracking, safe ingredients, and immutable order history. | • Create schema.sql (v2) • Create seed.sql with meals, ingredients • Enable RLS on all user tables • Deploy to Supabase | • All 15 tables created with RLS • Seed data loads without error • RLS blocks cross-user reads | Supabase project | 8 | Zero migration errors; seed loads in <5s
Sign In / Sign Up | As a new user, I can create an account; as a returning user I can log in and be routed to the correct screen. | • Auth screen with toggle (Log In / Sign Up) • Email + password fields • Name field on sign-up • Connect to Supabase Auth • Redirect logic: new → onboarding, returning → home | • Sign up creates Supabase user + profile row • Sign in routes to (tabs) • New user routes to onboarding • Loading state shown during auth | Supabase Auth, profiles table | 5 | Sign-up conversion rate; auth error rate
Onboarding Flow | As a new user, I can tell PawBowl about my pet so that meal recommendations are tailored to them. | • Pet type screen (dog / cat waitlist) • Dog setup form (name, breed, birth date, weight, sex, activity) • Save pet to Supabase • Mark user as onboarded | • Pet saved to pets table with pet_type_id • Cat → waitlist screen shown • Onboarding only shown once | Sign In / Sign Up, pets table | 5 | Onboarding completion rate; drop-off per step
Browse Pre-Made Meals | As a user, I can browse a catalogue of chef-crafted meals and see nutritional info so I can choose the right food for my pet. | • Meals list with search & filter • Meal cards with emoji, badge, calories, price • Filter by life stage (puppy/adult/senior) • Add to cart from card • Meal detail sheet | • 7+ meals shown from seed data • Filter reduces list correctly • Cart updates on add | meals table, seed data | 5 | Meal page views; add-to-cart rate per meal
Build-a-Bowl Wizard | As a user, I can build a fully custom meal by selecting ingredients step-by-step and see a live nutrition summary. | • 4-step wizard: protein → base → vegetable → booster • Live calorie + macro counter • Price preview • Save recipe to custom_recipes • Add to cart | • All 4 steps complete before allowing save • Macros update live • Saved recipe appears in profile | ingredients table, custom_recipes table | 8 | Wizard completion rate; avg time to build; recipes saved
Cart & Checkout | As a user, I can review my cart and place an order for my pet's food. | • Cart context (add/remove/quantity) • Cart screen with item list and total • Checkout form (address, delivery date) • Submit order to API • Order confirmation screen | • Cart persists across tabs • Order saved to orders + order_items • Confirmation shows order ID | orders table, pets table | 5 | Cart abandonment rate; checkout completion rate
Order History | As a user, I can view my past orders and quickly reorder a previous meal. | • Orders tab with list • Status badge (pending/processing/shipped/delivered) • Reorder button adds items back to cart • Last order shown on home screen | • All past orders shown newest-first • Reorder populates cart correctly | orders table, order_items table | 3 | Reorder rate; order frequency
Pet Profile (CRUD) | As a user, I can manage my pet's profile so that PawBowl always has accurate information. | • Profile tab with pet list • Add pet form • Edit pet inline • Delete pet with confirmation • Display: name, breed, age, weight, activity | • CRUD reflects in Supabase • Age auto-calculated from birth_date • Multiple pets supported | pets table, profiles table | 5 | Profile completion rate; number of pets per user
Pet Allergies & Health Goals | As a user, I can log my pet's allergies and health goals so that unsafe meals are flagged. | • Allergy picker (from ingredient catalogue + free-text) • Health goal multi-select (weight loss, skin coat, joints, etc.) • Save to pet_allergies + pet_health_goals • Show on pet profile card | • Allergies stored with severity • Health goals stored per pet • UI shows current selections | pet_allergies, pet_health_goals tables | 5 | Allergy entry rate; avg goals per pet
Meal Recommendations | As a user, I receive meal suggestions tailored to my pet's allergies, health goals, and life stage. | • Backend recommendation endpoint • Filter by pet_allergies (exclude flagged ingredients) • Boost by matching health goal tags • Filter by pet life_stage • 'Recommended for [pet name]' section on home | • Allergic ingredients excluded • Results differ per pet • Endpoint responds in <200ms | meal_ingredients, pet_allergies, pet_health_goals | 8 | Recommendation click-through rate; order rate from recommendations
Nutrition Dashboard | As a user, I can see a nutrition breakdown for any recipe so I know my pet is getting balanced meals. | • recipe_nutrition view in Supabase • Protein/fat/fiber/calorie rings • AAFCO minimum targets overlay • Visible on meal detail + custom recipe screens | • Macros match seed data • Rings fill proportionally • Below-target shown in amber/red | recipe_nutrition view, meals, meal_ingredients | 5 | Nutrition view engagement; avg macro balance score
Ingredient Safety Warnings | As a user building a bowl, I am warned if I add an ingredient that is unsafe or over-dosed for my pet. | • ingredient_rules enforcement in bowl wizard • Warning modal on adding flagged ingredient • Max-dose warning (e.g. spinach >1oz) • Forbidden ingredient blocks add | • Spinach over-dose triggers warning • Forbidden ingredient cannot be added • Warning shows severity (warning/danger) | ingredient_rules table | 5 | Warning show rate; user override rate; safety incident rate
Subscriptions / Auto-Reorder | As a user, I can subscribe to a recurring delivery of my pet's favourite meals. | • Subscription setup (frequency, start date) • Active subscription management (pause/cancel) • Stripe payment integration • Auto-order creation job | • Subscription creates recurring orders • Pause stops auto-orders without cancellation • Stripe webhook confirms payment | orders, Stripe | 13 | Subscription conversion rate; churn rate; MRR
Delivery Tracking | As a user, I can see where my order is and when it will arrive. | • Status timeline (placed → processing → shipped → delivered) • Estimated delivery date • Push notifications on status change | • Status updates reflect order_items.status • Push sent within 1 min of status change | orders, push notification service | 8 | Notification opt-in rate; CSAT on delivery
Reviews & Ratings | As a user, I can rate and review meals I have ordered. | • Star rating (1–5) per meal per order • Optional written review • Average rating shown on meal card • Moderation queue | • Only ordered meals can be reviewed • One review per meal per user • Average updates after new review | orders, meals | 5 | Review rate; avg rating per meal; review volume
Loyalty Points & Referrals | As a user, I earn points for purchases and can refer friends for bonus points. | • Points awarded per dollar spent • Referral code generation • Referral tracking • Points redemption at checkout | • Points update after order delivered • Referral credit only after referee's first order • Redemption reduces order total | orders, loyalty_points, referrals tables | 8 | Referral conversion rate; loyalty redemption rate; LTV uplift
Cat Meals & Ingredients | As a cat owner, I can access a cat-appropriate meal catalogue and build cat-safe custom bowls. | • ingredient_pet_types enables cat-safe subset • Cat meal catalogue (separate from dog) • ingredient_rules for cat-specific toxins • Onboarding routes cat owners to cat catalogue | • Cat meals only show cat-safe ingredients • Toxic-to-cats ingredients blocked • Cat waitlist converts to full access | pet_types, ingredient_pet_types | 13 | Cat waitlist conversion; cat meal order rate

## Sprint Tracker
🐾 PawBowl — Sprint Tracker
Sprint | Goal | Tickets | Points | Status | Notes
S0 | Database & Infrastructure | Schema v2 migration Seed data load Supabase RLS policies CI pipeline setup | 13 | Done | All tables created; seed loads; RLS verified
S1 | MVP Mobile App | Sign In / Sign Up screens Onboarding flow Home + Meals + Build tabs Cart & Checkout Order History Pet Profile CRUD | 36 | In Progress | Mock mode active; Supabase auth connection pending
S2 | Personalization | Allergy & health goal UI Recommendation engine Nutrition dashboard Ingredient safety warnings | 26 | Planned
S3 | Subscriptions | Subscription setup UI Stripe integration Delivery tracking Push notifications | 21 | Planned | Stripe account needed
S4 | Social & Loyalty | Reviews & ratings Loyalty points Referral system | 18 | Planned
S5 | Cat Support | Cat ingredient catalogue Cat meal catalogue Cat-specific safety rules Waitlist conversion flow | 16 | Planned

## KPIs
🐾 PawBowl — Key Performance Indicators
Category | KPI | Target (Month 3) | Target (Month 6) | Notes
Acquisition | New Signups | 500 | 2,000 | Email/password; referral bonus amplifies
Acquisition | Onboarding Completion Rate | 70% | 80% | % of signups who complete pet setup
Acquisition | Referral Conversion Rate | 15% | 25% | % of referred users who sign up
Engagement | DAU / MAU Ratio | 20% | 35% | Daily vs monthly active users
Engagement | Meals Browsed per Session | 4 | 6 | Average meals viewed per app session
Engagement | Custom Bowls Built per User | 1.5 | 3.0 | Avg custom recipes saved per account
Engagement | Allergy/Goals Profile Complete | 40% | 65% | % users who filled allergy/health goals
Revenue | Orders per Active User / Month | 1.2 | 2.0 | Target: ~weekly cadence by M6
Revenue | Average Order Value (AOV) | $28 | $34 | Meal + booster attach rate drives this up
Revenue | Subscription Conversion Rate | 10% | 25% | % users who start a recurring subscription
Revenue | Monthly Recurring Revenue | $1,500 | $12,000 | Based on subscription + reorder mix
Retention | 30-Day Retention | 45% | 60% | Users ordering again within 30 days
Retention | Churn Rate (subscriptions) | <8% | <5% | Monthly cancellation rate
Satisfaction | Average Meal Rating | 4.2★ | 4.5★ | Target maintained as catalogue grows
Satisfaction | NPS Score | 30 | 50 | Net Promoter Score via post-delivery survey
Safety | Ingredient Warning Override Rate | <5% | <3% | % users who ignore safety warnings
Safety | Auth Error Rate | <1% | <0.5% | Failed sign-in / sign-up per attempt